## Sheet3
| Color Meaning | Color
Done
On track
Delayed
|  |  | Thought of Idea | Team Meeting 1 | Status Report - Future Plan | Team Meeting 2 | Executive Summary | Team Meeting 3 | Update of Report | Executive Summary | Draft Report - Presentations submitted | Project Presentation by team | Final reports with code and Analysis
N. | Tasks Breakout | Status | 2019-10-07 | 2019-10-11 | 2019-10-14 | 2019-10-18 | 2019-10-21 | 2019-11-01 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-02 | 2019-12-09
Project planning
1 | Formed teams | Done
2 | Think of idea | Done
3 | Submit a plan | Done
4 | Roles and Responsabilities | Done
5 | Status report | Done
6 | Executive Summary | Done
7 | Update Report | Pending
8 | Draft Report | Pending
9 | Project Presentation | Pending
10 | Final report - Code and Analysis | Pending
11 | Presentation | Pending
12 | Code Planning | Pending
12 | Understanding the problem | Done
12 | Data Acquisition | Done
12 | Text Preprocessing | Done
12 | Text Parsing - EDA | Pending
12 | Text Representation | Pending
12 | Modeling Research | Pending
12 | Modeling - Pattern mining | Pending
12 | Model Evaluation | Pending
12 | Model Visualization | Pending
12
12